EIM Participating Resource Readiness Overview Checklist

Use this checklist to prepare for participation in the California ISO’s EIM Market

| Complete | Activity | Date |
| --- | --- | --- |
| Create a New Resource Implementation Project Each new EIM Participating Resource must establish a project that will be used for both market simulation and production. Once the project is created, the EIM Participating Resource will submit the required documents and information associated with their resources. Please refer to the New Resource Implementation Guide for information on the definition of a project and specific detailed timelines: |  |  |
| ☐ | Complete the ISO Initial Contact Information Request Form and submit it to NRI@caiso.com |  |
|  | The ISO NRI group will send you a project tracking number and Project Details Form to be filled out and returned to NRI@caiso.com |  |
| Select a Scheduling Coordinator for the EIM Market Each EIM Participating Resource will need to select a Scheduling Coordinator (SC) to participate in the EIM Market. An overview of the instructions and qualifications for becoming your own SC Scheduling Coordinator can be found in the SC certification Overview document. Additional information can be found in the SC Certification Business Practice Manual (BPM). |  |  |
| ☐ | Review and select from the list of current Scheduling Coordinators on the ISO web site an organization to represent you in the EIM market. *If you already have an established SC proceed to the next step Note: Only those Scheduling Coordinators with a value populated in the second column (Scheduling Coordinator SCID) are eligible to represent your resource in the EIM market |  |
| ☐ | Enter into an agreement with your Scheduling Coordinator and have them complete and send you the New SC Acceptance Letter. |  |
| ☐ | Complete the Resource Owner SC Selection Letter. |  |
| ☐ | The EIM Participating Resource must submit both the Resource Owner SC Selection Letter and the New SC Acceptance Letter to NRI@caiso.com using the file naming convention contained on page 5 of the New Resource Implementation Guide and the document title on page 12. Be sure to include your ISO project tracking number in the subject line of the email to New Resource Implementation when submitting these documents. |  |
| Submit an Initial Generator Resource Data Template (GRDT) Each EIM Participating Resource must complete and submit an initial GRDT containing resource specific characteristics. *Note: All new resources must submit an initial GRDT a minimum of 90 days prior to the activation date. |  |  |
| ☐ | To gain familiarity with the GRDT, review the GRDT Definitions file. |  |
| ☐ | Download and complete the Generator Resource Data Template for Energy Imbalance Market – version 8.0 under the Implementation section |  |
| ☐ | Complete the initial EIM GRDT for generators that will be participating in the EIM market. Note: Information sessions on how to complete an initial GRDT will be held during the late February to early March time frame. Information on these sessions will be communicated as it becomes available. |  |
| ☐ | The EIM Participating Resource must submit the Initial GRDT to NRI@caiso.com using the file naming convention contained on page 5 of the New Resource Implementation Guide and the document title on page 11. Be sure to include your ISO project tracking number in the subject line of the email to New Resource Implementation when submitting this document. |  |
| Register all Gas Resources with the California Air Resources Board (CARB) Each EIM Participating Resource must register all gas units with CARB that were utilized in the previous calendar year. *Note: Registration with CARB is not required for market simulation and only applies to Gas units actually producing energy utilized in California during the previous year. |  |  |
| ☐ | Due date for electric power entities to register specified facilities outside California, http://www.arb.ca.gov/cc/reporting/ghg-rep/ghg-rep-power/ghg-rep-power.htm | Feb 1, 20XX |
| ☐ | Reporting deadline for submitting Annual Emissions Data Reports for each Electric Power Entity. | June 1, 20XX |
| ☐ | Final verification statements due for all emissions data reports that contain imports, exports, or wheels under the MRR. | Sept 1, 20XX |
| ☐ | Register to report in Cal e-GGRT. The California Electronic Greenhouse Gas Reporting Tool (Cal e-GGRT) must be used for submitting annual GHG data reports. The Cal e-GGRT website may be accessed from the ARB Mandatory Reporting website, http://www.arb.ca.gov/cc/reporting/ghg-rep/ghg-rep.htm or directly from this link, https://ssl.arb.ca.gov/Cal-eGGRT/login.do All mandatory reporting of GHG emissions must occur via the Cal e-GGRT reporting tool. Email GHGreport@arb.ca.gov for detailed instructions. Note: Key Dates for MRR, http://www.arb.ca.gov/cc/reporting/ghg-rep/ghg-rep-dates.htm and MRR site, http://www.arb.ca.gov/cc/reporting/ghg-rep/ghg-rep.htm | On-Going |
| ☐ | Register for the Cap-and-Trade Program by registering with CITSS | On-Going |
| Scheduling Coordinator: Obtain Application Access for EIM Specific applications Each EIM Participating Resource must submit base load schedules into the EIM Base Schedule Aggregation Portal (BSAP). Each EIM Participating Resource may submit bids into the Real Time (RT) market via the SIBR application. Results are visible in the CMRI and OASIS applications. Access to ISO EIM applications can be obtained via the Access Identity Management (AIM) application. |  |  |
| ☐ | The Scheduling Coordinator point of contact must access the AIM application to create new user certificates and/or provision access EIM applications. Instructions can be found in the Access Identity Management (AIM) User Guide. Access to other ISO applications can be completed by submitting an Application Access Request Form. |  |