## Agreement Checklist
Company Name ¦ Track 2 - Agreements Checklist
Legend ¦ Task Owner: |  | EIM Entity | Transmission Side | Merchant Side | ISO
Target Activation Date:
Send all Emails to: SCRequests@caiso.com
All documents must be submitted via CIDI. If you do not have access to CIDI, please contact your UAA. The procedure to submit CIDI documentation can be found here:
http://www.caiso.com/Documents/How-to-Submit-Documentation-for-Applications-and-Ongoing-Obligations.pdf
Note: EDAM Scheduling Coordinators are required to have contracts already established with the CAISO. If potential EDAM SC does not have agreements, or to verify if selected SC agent has correct agreements, please email SCReqeusts@caiso.com to confirm requirements and determine next steps. To apply to become a scheduling coordinator, please review our Scheduling Coordinator Certification BPM:
https://bpmcm.caiso.com/Pages/BPMDetails.aspx?BPM=Scheduling%20Coordinator%20Certification%20and%20Termination
If SC would like to obtain a new SCID for EDAM purposes, please review the additional SCID process:
http://www.caiso.com/Documents/ExistingSchedulingCoordinatorRequestsAdditionalSCID-Procedure.pdf
| Task Name/ Pro Forma Agreements | Responsible | Timeline | Target Date | Completion Date | Status | Comments
1 | Confirm Scheduling Coordinator Company, does company have SC Agreements set up? | All | T-10M |  |  | Not Started | Marked complete once verification of SC Agreements are completed. Name of scheduling Coordinator:
2 | EDAM Implementation Agreement | Entity | T-19M |  |  | Not Started | Can be executed earlier, T-19M is the no later than date. https://www.caiso.com/Documents/EDAMEntityImplementationAgreementInformationRequestSheet.doc
3 | EDAM Load Serving Entity Agreement | Merchant Side | T-10M |  |  | Not Started | Can select WEIM PRSC Agent. If a new SCID is required, please see note above for link.
| EDAM Load Serving Entity Info Sheet | Merchant Side | T-10M |  |  | Not Started | https://www.caiso.com/Documents/EDAMLoadServingEntityAgreementInformationRequestSheet.doc
| CLAP: NRI Project Details Form | Merchant Side | T-3M prior to market sim |  |  | Not Started | https://www.caiso.com/participate/Pages/NewResourceImplementation/Default.aspx
| CLAP: SQMD Plan Project Number: | Merchant Side | T-3M prior to market sim |  |  | Not Started
| CLAP: SQMD Plan Approved | Merchant Side | T-2M prior to market sim |  |  | Not Started
| Load Serving Entity Scheduling Coordinator Name | Merchant Side | T-14M |  |  | Not Started | SC must have the PRSC Agreement to represent EDAM LSE. Please provide the name of the SC or Company wishing to become an SC. To become an SC, please visit our webpage to get started: http://www.caiso.com/participate/Pages/BecomeSchedulingCoordinator/Defau
| Deliverable: Load Servicing Entity Agreement | ISO |  |  |  | Not Started
4 | EDAM Transmission Service Provider Agreement | Transmission | T-10M |  |  | Not Started | Must use WEIM Entity SCID
| EDAM Transmission Service Provider Agreement Info Sheet | Transmission | T-11M |  |  | Not Started | https://www.caiso.com/Documents/EDAMTransmissionServiceProviderAgreementInformationRequestSheet.doc
| Deliverable: EDAM Transmission Service Provider Agreement | ISO |  |  |  | Not Started
5 | EDAM Addendum to EIM Entity Agreement | Transmission | T-10M |  |  | Not Started
| EDAM Addendum EIM Entity Info Sheet |  | T-11M |  |  |  | https://www.caiso.com/Documents/EDAMAddendumtotheEIMEntityAgreementInformationRequestSheet.doc
| Deliverable: EDAM Addendum to EIM Entity Agreement | ISO |  |  |  | Not Started
6 | EDAM Addendum to EIM Entity SC Agreement | Transmission | T-10M |  |  | Not Started
| EDAM Addendum EIM Entity SC Info Sheet |  | T-11M |  |  |  | https://www.caiso.com/Documents/EDAMAddendumtotheEIMEntitySchedulingCoordinatorAgreementInformationRequestSheet.doc
| Deliverable: EDAM Addendum to EIM Entity SC Agreement | ISO |  |  |  | Not Started
7 | EDAM Addendum to EIM Participating Resource Agreement | Merchant Side | T-10M |  |  | Not Started
| EDAM Addendum EIM Participating Resource Agreement Info Sheet |  | T-11M |  |  |  | https://www.caiso.com/Documents/EDAMAddendumtotheEIMParticipatingResourceAgreementInformationRequestSheet.doc
| Updated Schedule 1 with Regulatory Contracts for participating resources |  | T-10M |  |  | Not Started | Email RegulatoryContracts@caiso.com to obtain current schedules to redline
| Deliverable: EDAM Addendum to EIM Participating Resource Agreement | ISO |  |  |  | Not Started
8 | EDAM Addendum to EIM Participating Resource SC Agreement | Merchant Side | T-10M |  |  | Not Started
| EDAM Addendum EIM Participating Resource SC Info Sheet |  | T-11M |  |  | Not Started | https://www.caiso.com/Documents/EDAMAddendumtotheEIMParticipatingResourceSchedulingCoordinatorAgreementInformationRequestSheet.doc
| Deliverable: EDAM Addendum to EIM Participating Resource SC Agreement | ISO |  |  |  | Not Started
9 | Dynamic Schedule Resources | Merchant Side | T-10M |  |  | Not Started | Please provide a list of resource IDs that are dynamically scheduled. If no resource IDs, please send confirmation of no scheduled resources.
Does the EDAM BAA include Dynamically Scheduled Resources into the CAISO? If so list the resources
10 | Optional Agreement: Convergence Bidding Entity Agreement | Merchant Side | T-2M |  |  | Optional | This is an optional agreement and not required to complete EDAM onboarding. http://www.caiso.com/Documents/RegistrationForm_ConvergenceBiddingEntityAgreement.doc
Convergence Bidding Info Sheet
| Deliverable: Convergence Bidding Entity Agreement | ISO |  |  |  | Optional
11 | Optional Agreement: Meter Service Agreement Scheduling Coordinator | Both | Optional |  |  | Optional | Confirm MSASC is on file. If on file, this is not needed.
| Meter Service Agreement Info Sheet |  | T-2M |  |  | Optional | http://www.caiso.com/Documents/MeterServiceAgreement_SchedulingCoordinatorsInformationRequestSheet.doc
| Deliverable: Meter Service Agreement Scheduling Coordinator | ISO |  |  |  | Optional
12 | Financial review | Entity | T-3M |  |  | Not Started | • EDAM entity will provide requested financial documentation and financial review via CIDI or by email to cbilling@caiso.com. • Documentation can be submitted no earlier than 12 months in advance of Market Sim date. • This will follow the 2 year audit review for finance per the CAISO Tariff. If EDAM Entity has already completed a financial review within the last 24 months, this step is not required.
ISO Tasks
ISO | EDAM Role Matrix | ISO | T-11M |  |  | Not Started | Used to provision roles
ISO | EDAM Role Matrix Training | ISO | T-10M |  |  | Not Started

## Data
Status
Not Started
In Progress
Delayed
N/A
Complete